## 1stqtr2021
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE FIRST QUARTER, CY 2021
Province, City or Municipality: MIAGAO
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extensions, if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
I. Social Development
1. Purchase/Construction and Improvement of Government Facilities-Social Development
1. Assistance to Barangays
a. Construction/Rehabilitation of Manpower
Development Center (Barangay Plaza)
1. Barangay Alimodias | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
2. Barangay Nam-o Sur | Miagao, Iloilo | 350000 |  |  | 0% |  |  | not implemented
3. Barangay Baraclayan | Miagao, Iloilo | 80000 |  |  | 0% |  |  | not implemented
4. Barangay Cubay | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
5. Barangay Narorogan | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
6. Barangay Bacolod | Miagao, Iloilo | 300000 |  |  | 0% |  |  | not implemented |  | 300000
7. Barangay Pudpud (2 Sitios) | Miagao, Iloilo | 140000 |  |  | 0% |  |  | not implemented
8. Barangay Kirayan Tacas | Miagao, Iloilo | 150000 |  |  | 0% |  |  | not implemented
9. Barangay Olango | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
b. Construction/Rehabilitation of Multi-Purpose Hall/
Building
1. Barangay Nam-o Norte (covered gym) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
2. Barangay Durog (Multi-Purpose Hall) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
3. Barangay Ubos Ilawod | Miagao, Iloilo | 60000 |  |  | 0% |  |  | not implemented
4. Barangay Tigmalapad (Health Center) | Miagao, Iloilo | 50000 | 2021-03-30 |  | 100% | 50000 |  | completed
5. Barangay San Jose (Day Care Center) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
6. Barangay Bacauan (Day Care Center) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
7. Barangay Maninila (Day Care Center) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
FDP Form 7 - 20% Component of the IRA Utilization
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extensions, if
|  |  |  | Date | Completion | Incurred to Date | any | Remarks
8. Barangay Narorogan (Tanod Outpost) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
9. Barangay Cabunotan | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
10. Barangay Tan-agan | Miagao, Iloilo | 100000 | 2021-03-03 |  | 100% | 100000 |  | completed
11. Barangay Tigmalapad | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
c. Construction/Rehabilitation of Water Supply System
1. Barangay Ilog-ilog | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
2. Barangay Awang | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
3. Barangay Malagyan | Miagao, Iloilo | 140000 |  |  | 0% |  |  | not implemented
4. Barangay Bolocaue | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
5. Barangay Igsoligue | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
6. Barangay Potrido | Miagao, Iloilo | 200000 |  |  | 0% |  |  | not implemented
7. Barangay Buenavista Norte | Miagao, Iloilo | 80000 |  |  | 0% |  |  | not implemented
II. Economic Development
1. Agriculture and Fishery Development
1.1Construction/Rehabilitation of Irrigation Facilities | Miagao, Iloilo | 500000 |  |  | 0% |  |  | not implemented
2. Purchase/Construction and Improvement of Government Facilities-Economic Development
2.1 Construction of UPV Miagao Circumferential Road | Miagao, Iloilo | 5000000 | 2021-03-17 |  | 0% |  |  | with PR-
Php5,000,000.00
2.2 Construction of Igdalaquit Overflow Bridge | Miagao, Iloilo | 500000 |  |  | 0% |  |  | not implemented
2.3 Rehabilitation of Diday-Tambong Road | Miagao, Iloilo | 1500000 |  |  | 0% |  |  | not implemented
2.4 Opening of Buenavista Norte-San Fernando Road | Miagao, Iloilo | 1000000 |  |  | 0% |  |  | not implemented
FDP Form 7 - 20% Component of the IRA Utilization
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extensions, if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
2.5 Construction of Calagtangan-Buenvaista Norte | Miagao, Iloilo | 300000 |  |  | 0% |  |  | not implemented
Hanging Bridge
2.6 Construction of Dalije Overflow Bridge | Miagao, Iloilo | 1000000 |  |  | 0% |  |  | not implemented | 1000000
2.7 Construction of Cabalaunan Hanging Bridge | Miagao, Iloilo | 1000000 |  |  | 0% |  |  | not implemented
2.8 Construction of Public Market Building (Drainage | Miagao, Iloilo | 3000000 |  |  | 0% |  |  | not implemented
System, Pavement, Fencing)
2.9 Fencing and Concreting of Pavement of Food Terminal | Miagao, Iloilo | 2000000 |  |  | 0% |  |  | not implemented
2.10 Concreting of Road to Evacuation Center at | Miagao, Iloilo | 1500000 |  |  | 0% |  |  | not implemented
Barangay Baybay Norte
2.11 Construction of Fence/Enclosure of Evacuation | Miagao, Iloilo | 1500000 |  |  | 0% |  |  | not implemented
Center at Baybay Norte
2.12 Construction of Fence of Evacuation | Miagao, Iloilo | 1500000 |  |  | 0% |  |  | not implemented
Center at Kirayan Tacas
2.13 Completion of Evacuation Center at Kirayan Tacas | Miagao, Iloilo | 3000000 |  |  | 0% |  |  | not implemented
(Water System, Pavements, Electricals, etc.)
2.14 Construction of Stairs with Railings at Bugsukan Falls | Miagao, Iloilo | 400000 |  |  | 0% |  |  | not implemented
2.15 Construction of Access Road (Igtuba-ISAT-U) | Miagao, Iloilo | 3000000 | 2021-03-17 |  | 0% |  |  | with PR-
Php3,000,000.00
FDP Form 7 - 20% Component of the IRA Utilization
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extensions, if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
2.16 Loan Amortizaion - Market | Miagao, Iloilo | 6200000 | 2021-03-22 |  | 19.66% | 1218749.42
2.17 Assistance to Barangays | Miagao, Iloilo
a. Construction/Rehabilitation of Hanging Bridge
1. Barangay Olango (Footbridge) | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
2. Barangay Cagbang | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
3. Barangay Bariri | Miagao, Iloilo | 60889 |  |  | 0% |  |  | not implemented
4. Barangay Oya-oy | Miagao, Iloilo | 500000 |  |  | 0% |  |  | not implemented
b. Construction/Rehabilitation of Roads and Footwalk
1. Barangay Igcabidio (Footwalk) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
2. Barangay Cabalaunan (Footwalk) | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
3. Barangay Naulid (Footwalk) | Miagao, Iloilo | 150000 |  |  | 0% |  |  | not implemented
4. Barangay Cagbang (Footwalk) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
5. Barangay Tig-amaga (Footwalk) | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
6. Barangay Cubay (Footwalk) | Miagao, Iloilo | 70000 | 2021-03-24 |  | 100% | 70000 |  | completed
7. Barangay Bolocaue (Footwalk) | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
8. Barangay Dalije | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
9. Barangay Bagumbayan | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
10. Barangay Damilisan | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
11. Barangay Bacauan | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
12. Barangay Pungtod Monteclaro | Miagao, Iloilo | 200000 |  |  | 0% |  |  | not implemented
III. Environmental Management
1. Purchase of Pyrolysis Machine | Miagao, Iloilo | 3000000 |  |  | 0% |  |  | not implemented
FDP Form 7 - 20% Component of the IRA Utilization
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost | Extensions, if | Remarks
|  |  |  | Date | Completion | Incurred to Date | any
2. Assistance to Barangays
a. Construction of Sea/River Wall Protection/Gabion
a.1 Barangay Bugtong Naulid | Miagao, Iloilo | 100000 |  |  | 0% |  |  | not implemented
a.2 Barangay Mambatad | Miagao, Iloilo | 70000 |  |  | 0% |  |  | not implemented
We hereby certify that we have reviewed the contents and hereby attest to the veracity and
correctness of the data or information contained in this document.
( Sgd.) JANE N. VALENZUELA |  |  |  |  | ( Sgd.) MACARIO N. NAPULAN, M.D.
Municipal Budget Officer | [5 empty] | Municipal Mayor
Social Dev't | 2890000
Economic Dev't | 34770889
Environmental Mgmt | 3170000
40830889
#REF!
#REF!
#REF!