## Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECT, PROGRAMS, or ACTIVITIES
FOR THE 2nd QUARTER 2021
Province, City or Municipality: Miagao
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if Any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
BUB Integrated Community Food Production (ICFP) Project | Miagao, Iloilo | 2100000 | December 2015 | December 2016 | 52.43% | 1101088.77
Multi-Purpose Hall, Brgy. Damilisan, Miagao, Iloilo | Brgy. Damilisan Miagao, Iloilo | 200000 | September 2015 |  | 0% | 0
Philhealth Capitation fund DOH 3rd & 4th qtr. 2014 & 2015 | Miagao, Iloilo | 2056375 | November 2016 | December 2017 | 69.59% | 1431021.64
Brgy. Food Terminal ( Brgy. Dawog, Igbugo, Igdalaquit & La Consolacion) | Miagao, Iloilo | 1405870 | January 2017 | December 2020 | 73.05% | 1027033.8
Technology Training on Garlic and Onion Production, Post Harvest and Marketing Training | Miagao, Iloilo | 1169000 | January 2017 | December 2018 | 65.79% | 769065.5
Purchase of Relocation Site Sitio Pay Hudan | Miagao, Iloilo | 300000 | Septemebr 2017 | December 2018 | 0%
Livelihood Program to Livelihood Project | Miagao, Iloilo | 3440000 | December 2017 | December 2018 | 92.84% | 3193705.55
Construction of Food Terminal/Trading Post | Slaughterhouse Compound, Miagao, Iloilo | 900000 | January 2019 | December 2019 | 75.08% | 675750
Multi-Purpose Teen Center Palaca-Damilisan NHS | Brgy. Tabunacan Miagao, Iloilo | 300000 | January 2019 |  | 0%
Upgrading/Rehabilitation/Repair of BHS | Miagao, Iloilo | 2700000 | September 2019 | December 2020 | 89.03% | 2403719.71
Construction of Multi -Purpose JRBB Hall | Miagao, Iloilo | 965000 | December 17, 2019 | December 2020 | 87.61% | 845427
Construction of Dike Brgy. Maninila | Brgy. Maninila, Miagao, Iloilo | 3560000 | January. 17, 2020 | December 2021 | 51.51% | 1833892.64
Construction of River Bank Brgy. Frantilla & Paro-on | Brgy. Frantilla & Brgy. Paro-on , Miagao, Iloilo | 3060000 | January. 17, 2020 | December 2021 | 22.49% | 688211.56
Construction of Slope Protection Brgy. Cagbang | Brgy. Cagbang, Miagao, Iloilo | 3780000 | January. 17, 2020 | December 2021 | 61.66% | 2330682.21
Purchase of Monoblock Chair Liga ng nga Barangay | Miagao, Iloilo | 1210000 | February 10, 2020 | December 2021 | 99.9% | 1208800
Construction of Brgy. Oyungan Senior Cittizen Center | Brgy. Oyungan, Miagao, Iloilo | 200000 | February 10, 2020 | December 2021 | 84.14% | 168272
Concreting of Access Road Brgy. Dingle & Retaining Wall Brgy. Wayang | Brgy. Dingle, Miagao, Iloilo | 1040000 | February 10, 2020 | December 2021 | 98.25% | 1021804.16
Construction of Water System Brgy. Sag-on | Brgy. Sag-on, Miagao, Iloilo | 1300000 | February 10, 2020 | December 2021 | 99.12% | 1288542.55
Construction of Solar Lights Tumagbok- Plaza | Miagao, Iloilo | 300000 | February 28, 2020 | December 2021 | 0% | 0
F/A Various Social Activities( Salakayan 2020 | Miagao, Iloilo | 300000 | March 5, 2020 | February 2020 | 83.67% | 251010
Construction of Camp. Monteclaro Multi-Purpose Bldg. Including Pavement | Miagao, Iloilo | 4000000 | March 3, 2020 | December 2021 | 0% | 0
Construction of Bacolod Elementary School Multipurpose Building including Pavement | Miagao, Iloilo | 4000000 | March 3, 2020 | December 2021 | 0% | 0
Financial Assistance for the Installation/maintenance of Quarantine facility | Miagao, Iloilo | 1000000 | August 2020 | December 2020 | 77.98% | 779845
Completion of RHU II | Brgy. Guibungan, Miagao, Iloilo | 1050000 | September 2020 | December 2021 | 21.07% | 221210.48
Upgrading of Sitio Gines, Palaca- Buenavista-Tugura-ao Road | Miagao, Iloilo | 4334000 | November 2020 | December 2021 | 0%
Completion of RHU 1 | Municipal Compound, Miagao, Iloilo | 3381000 | December 2020 | December 2021 | 21.34% | 721454.56
Construction of Solar Lights UPV Junction Box - to Brgy. Mambatad | Miagao, Iloilo | 300000 | January 22, 2021 | December 2021 | 0%
Hanging Bridge Brgy. Naclub | Brgy. Naclub, Miagao, Iloilo | 3650000 | March 11, 2021 | March 2022 | 0%
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
( Sgd.) MAYLENE T. SERVIDAD | [5 empty] | ( Sgd.) HON. MACARIO N. NAPULAN, M.D.
Local Accountant | [5 empty] | LCE
Note on A12: ACCOUNTING: with 2nd tranche 575, 070.00